## Sheet1
Week | Task | Difficulty
2021-10-04 | Create a Project Plan | Easy
| Create a Trello board for the project | Easy
| Create a project timeline worksheet | Easy
2021-10-11 | Get Started | Medium
| Create a Git Repository | Easy
| Copy Flask Code to the Project | Medium
2021-10-18 | Perform Initial Tests | Medium
| Verify that the app runs in the local env successfully | Medium
| Verify that the app runs on the Cloud shell successfully | Medium
2021-10-25 | Deploy the app using GitHub Actions | Hard
| Set up GitHub Actions | Medium
| Create the App service in Azure cloud | Medium
| Validate that the app is running in the Azure cloud. | Easy
2021-11-01 | Deploy the app using Azure Pipeline | Hard
| Set up the Azure DevOps pipeline | Hard
| Run the pipeline | Easy
2021-11-08 | Complete Documentation - including screenshots | Medium
| Create architectural diagram | Easy
| Take screenshots demonstrating key steps | Easy
| Create README file with instructions on how to run the code | Easy
| Create demo video and post to YouTube | Medium
Q4 plan | Complete the project
Yearly plan | Perform periodic Review of the insfrastrure and the application and validate